## Sheet1
TASK NAME | ASSIGNED TO | SUB TASKS | END DATE | STATUS
Machine Learning | Ahmed Elsharabasy | Collect data by web scrabing & Data preprocessing | 2023-07-03 | Completed
|  | Model ML | 21/3/2023 | Completed
|  | Deployment Model to website/app (MLOPs) | 2023-04-04 | In Progress
|  | Part of documentation | 2023-11-04
UI/UX | Mazen Elalfy | UI pages | 2023-04-04 | In Progress
Application | Mohammed Nasr / Sama | UI pages | 2023-11-04 | In Progress
|  | API | 25/4/2023 | In Progress